## Sheet1
Milestone | Task | Best | Likely | Worst | Date/Work Hours
| Develop and document project plan | 1 | 1.5 | 3
Submit project plan |  |  |  |  | 2018-09-20
| Build environment setup | 0.5 | 0.5 | 1 | 0.61111
| Git repository | 1 | 1.5 | 2 | 1.5
| Initial makefile, main() and framework | 8 | 8 | 12 | 8.8889
| Basic command line prompt and parse | 4 | 6 | 6 | 5.5556
| Help function | 5 | 6 | 8 | 6.2222
Command prompt with help
| Allocate | 8 | 10 | 10 | 9.5556
| Free | 6 | 7 | 7 | 6.7778
| Display | 5 | 7 | 9 | 7
| Modify | 4 | 6 | 8 | 6
Display and modify
| Execution time measurement | 5 | 7 | 7 | 6.5556
| Invert | 4 | 6 | 8 | 6
Timed functions
| Experiments and writups | 10 | 11 | 14 | 11.4444
| Write pattern | 8 | 10 | 10 | 9.5556
| Verify pattern | 9 | 10 | 13 | 10.4444
Feature complete
| Final report | 5 | 7 | 10 | 7.2222
Submit final report
Project Partners
Mohit Rane
Suman Hosmane